## Sprint 1 Timeline
Task | Group or Individual? | 2019-10-08 | 2019-10-09 | 2019-10-10 | 2019-10-11 | 2019-10-12 | 2019-10-13 | 2019-10-14 | 2019-10-15 | 2019-10-16 | 2019-10-17 | 2019-10-18
Add operational requirements to SRS | Alex | bar: 2019-10-08
Class (UML Overview) | N/A | bar: 2019-10-08
Group Standup After Class | Group | bar: 2019-10-08
Source Code Release | N/A | bar: 2019-10-08
Digest Source Code | Individual | bar: 2019-10-08 to 2019-10-09
Sprint 1 Plan Due | Group | bar: 2019-10-09
UML and Architecture Meeting (6-7:30pm) | Group | bar: 2019-10-10
Vaibhav Office Hours (5-8pm) | N/A | bar: 2019-10-10
Planning Meeting (7:30-8pm) | Group | bar: 2019-10-10
Send first draft UML to Vaibhav | Group | bar: 2019-10-10
Install Tomcat | bar: 2019-10-11
HW2 Due @ Midnight | Individual | bar: 2019-10-11
Dedicated Study Days | N/A | bar: 2019-10-12 to 2019-10-14
In Class Exam | N/A | bar: 2019-10-15
Write Tests for existing code | Group | bar: 2019-10-16 to 2019-10-18
Sprint Review (8pm) | Group | bar: 2019-10-18

## Sprint 1 Goals
Core Goals | Stretch Goals
Understand code | Implement User->User Messaging
Code running on everyone's individual IDE
Tomcat installed on everyone's PC
Host on free platform (i.e. EC2)
UML and Architecture
Set up daily standup bot

## Notes on Testing Code
Notes from Meeting
Only need to write tests for the functions we write
No tolerance for code smells
Prof is looking for quality code over quantity
Focus on test driven development